## Milestones_BCA_ApplicationV1.0
S.No. | Milestones
Milestone-I
1 | Front & Back Mock Flow
2 | Dashboard UI
3 | QA & Fixes
4 | UAT & Fixes
5 | Database Diagram
6 | Deployment of Milestone-I
Milestone-II
1 | Booking Management: -> Job Booking -> Booking List -> Work Allocation -> Create Dockets -> Booking Dashboard
2 | Fleet Management -> Listing of Fleets -> Insert a Fleet -> Edit & Delete Fleet
4 | QA & Fixes
5 | UAT & Fixes
6 | Deployment of Milestone-II
Milestone-III
1 | Configurations -> Masters -> Driver -> Customer -> Site -> Supervisor -> Assest Group
2 | User Management (Staff)
3 | Role Configuration Module
4 | Import Module Note: It will be one time activity, before we live the application on your server. We will import all the details into the application. If in future you need to enter bulk data through import, then please share us we will do the same.
5 | QA & Fixes
6 | UAT & Fixes
7 | Deployment of Milestone-III
Milestone-V
1 | Invoices and Billing
2 | Workshop Module - Service and Repair
3 | QA & Fixes
4 | UAT & Fixes
5 | Deployment of Milestone-V
Milestone-VI
1 | Reports
2 | Dashboard
3 | QA & Fixes
4 | UAT & Fixes
5 | Deployment of Milestone-VI
Milestone-IV (Android Tablet - Application)
1 | Dashboard
2 | Booking Management (Work/Job Allocation)
3 | QA & Fixes
4 | UAT & Fixes
Milestone-VII
1 | Enquiry & Quote Module
2 | Compliance Module
3 | QA & Fixes
4 | UAT & Fixes
5 | Deployment of Milestone-VII
Milestone-VIII
1 | Final QA & Bug Fixes
2 | UAT & Fixes
3 | Final Deployment to Borg Civil Server